# JARAMOGI OGINGA ODINGA UNIVERSITY OF SCIENCE AND TECHNOLOGY

# SCHOOL OF AGRICULTURAL AND FOOD SCIENCES

UNIVERSITY EXAMINATION FOR DEGREE OF BACHELOR OF SCIENCE IN AGRIBUSINESS MANAGEMENT

3RD YEAR 1ST SEMESTER 2019/2020 ACADEMIC YEAR

RESIT

COURSE CODE: AAE 3312

COURSE TITLE: ANALYSIS AND PLANNING OF AGRICULTURAL PROJECTS

EXAM VENUE: 	STREAM: (BSc. Agribusiness Management)

DATE: 				            EXAM SESSION:

TIME:

Instructions

- Answer ALL questions in Section A (compulsory) and ANY TWO questions in Section B

- Candidates are advised not to write on the question paper

- Candidates must hand in their answer booklets to the invigilator while in the examination room

SECTION A		[30 MARKS]

Answer ALL questions in this Section.

- Project managers must engage in risk and uncertainty management to understand and control them in their projects.

(a)  Outline any four risks that might interfere with agricultural project

implementation.                                                                                                  [4marks]

(b)  Explain any four aspects considered in environmental analysis of agricultural

projects.                                                                                                               [4marks]

(c)  Differentiate between:

- A project and A plan                                                                               [1 mark]

- Ex-ante analysis and Ex-post analysis                                                  [1 mark]

- A project moves through stages. An idea germinates then it passes through various steps which will clarify the concept.

(a) Briefly explain the project life cycle.                                                                    [5marks]

(b) What are the main characteristics of agricultural projects?                                  [5marks]

- (a)  What are the limitations of Gantt chart as a planning technique in agricultural

projects.                                                                                                          [2marks]

(b)   Outline any three objectives of monitoring and evaluation in agricultural

projects                                                                                                            [3marks]

(c)   Explain any five technical aspects you would consider in a project

targeting implementation of cage fish farming in the Lake Victoria region.   [5marks]

SECTION B		[40 MARKS]

Answer any TWO QUESTIONS in this Section.

- Use the table below to answer the questions below.

| Activity | Predecessor | Duration (Days) |
| --- | --- | --- |
| A | - | 20 |
| B | A | 10 |
| C | B | 8 |
| D | A | 11 |
| E | C, D | 7 |
| F | E | 6 |
| G | D | 12 |
| H | E | 13 |
| I | G, H | 5 |

Required;

- Draw a network diagram.                                                                               [8 marks]

- Determine;

- Critical activities                                                                                     [2 marks]

- Critical path                                                                                             [2 marks]

- Project duration                                                                                       [2 marks]

(c)  Advise an agricultural project manager on how to treat labour abundance

In the face of capital intensive technology advocacy.                                   [ 6 marks]

- Financial analysis refers to cash-flows from which present and future expenditure and income are calculated to determine the financial feasibility of a project.

(a)  Briefly discuss the importance of this analysis with reference to agricultural projects.

[12 marks]

(b) A prospective investor is contemplating investing in two projects presented in the table below. Use the information below to advise him accordingly.

| Year | Investments | Returns from Project A |  | Returns from Project B |  |
| --- | --- | --- | --- | --- | --- |
| 1 | 20,000 | - |  | 12,000 |  |
| 2 | 8,000 | 8,000 |  | 9,000 |  |
| 3 | 6,500 | 12,000 |  | 5,500 |  |
| 4 | 2,500 | 20,000 |  | 6,000 |  |
| 5 | 1,000 | 10,500 |  | 25,000 |  |
| 6 | - | 8,000 |  | 20,000 |  |
| 7 | - | 9,500 |  | 17,500 |  |

Required:

(a) Calculate the payback period of each project.                                                         [6marks]

(b) Advise the investor on the best project to invest in. Justify your answer.               [2marks]

- With the government ban on plastic packaging materials, a local NGO has come up with a proposal of making packaging materials from the abundant papyrus reeds from the Yala swamp. The swamp supports different organisms and rare birds in danger of extinction. The NGO intends to target the small-scale traders with their products.

(a) As an agricultural project manager, advise them on the commercial and environmental

aspects of the project.                                                                                               [4marks]

(b) Is this project suitable for public or private funding? Justify your answer.             [2marks]

(c) Explain any two externalities that may be experienced in this project.                   [4marks]

(d) How would you classify this type of agricultural project?                                      [2marks]

(e) Briefly explain how this agricultural project may help the agricultural sector

contribute to the achievement of Vision 2030 under the economic pillar.                [2marks]

(f) Shadow prices are used when there are distortions in the market to determine

the scarcity value of goods and services used in the project. Outline some of the

general problems with the determination of shadow prices.                                   [6marks]